## Slide 1: Software Project Estimation (wideband Delphi estimation technique)

## Slide 2: What is Project Estimation?
How much will the project take in terms of time, cost, money and manpower?
For example, if we are designing a system . Following needs to be answered first,
  How many developers are needed?
  How many months will it take?
  What will be total project cist?
  What tools or infrastructure is needed?
After that project manager put forward the proposal for acceptance.

## Slide 3: Need for Project Estimation
  Budget planning
  Time scheduling
  Resource allocation
  Risk management
  Stake holders’ communication
  Project feasibility analysis

## Slide 4: Need for Project Estimation
Let’s say a team is building an LMS:
  Without estimation,
    Deadlines might be unrealistic
    Budget may exceed its limits
    Team might be insufficient
  With estimation
    Effort=1200 person-hours (1 person working for an hours)
    Duration = 4months
    Cost= PKR 1,200,000
    Team = 4 developers + 1 tester
Now, planning is structured and controlled.

## Slide 5: Estimation techniques
  COCOMO
  Wideband delphi estimation
  Functional points estimation
  LOC estimation

## Slide 6
For good estimation, following are needed:
  WBS
  deliverables
  A clear effort estimation for each task
  A list of assumptions which were necessary for making the estimate
  Consensus among the project team that the estimate is accurate

## Slide 7: Assumptions Make Estimates More Accurate
Team members make assumptions about the work to be done to deal with incomplete information
  Must estimate the issues needed to make decision
  Assumptions must be written down so that if they prove to be incorrect then it must be back tracked and corrected.

## Slide 8: Wideband Delphi
Wideband Delphi is a process that a team can use to generate an estimate
  The project manager chooses an estimation team,
  and gains consensus among that team on the results.
  Wideband Delphi is a repeatable estimation process because it consists of a straightforward set of steps that can be performed the same way each time

## Slide 9: Delphi Technique
Take inputs from multiple stake holders
Create final estimate on that
Steps followed:
  Must have a facilitator/coordinator
  Create list of experts
  Create 3-5 questions
    For example what's better to use for project? Azure / AWS etc..….
  Reach to all the results
  Analyze & iterate

## Slide 10: The Wideband Delphi Process
Step 1: Choose the team
  The project manager selects the estimation team and a moderator. The team should consist of 3 to 7 project team members.
    The moderator should be familiar with the Delphi process, but should not have a stake in the outcome of the session if possible.
    If possible, the project manager should not be the moderator because he should ideally be part of the estimation team.

## Slide 11: The Wideband Delphi Process
Step 2: Kickoff Meeting
  The project manager must make sure that each team member understands the Delphi process, has read the vision and scope document and any other documentation, and is familiar with the project background and needs.
  The team brainstorms and writes down assumptions.
  The team has the generated WBS.
  The team agrees on a unit of estimation.

## Slide 12: The Wideband Delphi Process
Step 3: Individual Preparation
  Each team member independently generates a set of preparation results.
  For each task, the team member writes down an estimate for the effort required to complete the task,
  and any additional assumptions he needed to make in order to generate the estimate.

## Slide 13: The Wideband Delphi Process
Step 4: Estimation Session
  During the estimation session, the team comes to a consensus on the effort required for each task in the WBS.
  Each team member fills out an estimation form which contains his estimates.
  The rest of the estimation session is divided into rounds during which each estimation team member revises her estimates based on a group discussion. Individual numbers are not discussed.

## Slide 14: The Wideband Delphi Process
Step 4: Estimation Session (continued)
  The moderator collects the estimation forms and plots the sum of the effort from each form on a line:

## Slide 15: The Wideband Delphi Process
Step 4: Estimation Session (continued)
  The team resolves any issues or disagreements that are brought up.
    Individual estimate times are not discussed. These disagreements are usually about the tasks themselves. Disagreements are often resolved by adding assumptions.
  The estimators all revise their individual estimates. The moderator updates the plot with the new total:
  Goal: to achieve the max Convergence.

## Slide 16: The Wideband Delphi Process
Step 4: Estimation Session (continued):
  The moderator leads the team through several rounds of estimates to gain consensus on the estimates. The estimation session continues until the estimates converge or the team is unwilling to revise estimates.
  Delta sheet could also be formed by showing the variation in estimates after a round.
Step 5: Assemble Tasks
  The project manager works with the team to collect the estimates from the team members at the end of the meeting and compiles the final task list, estimates and assumptions.
Step 6: Review Results
  The project manager reviews the final task list with the estimation team.

## Slide 17: Case study

## Slide 18: Solution