## Slide 1: Work Breakdown Structure

## Slide 2
SW
Project
SCOPE
Planning
Requirements
Design
Development
Testing
Built
Release
Scope and planning involves defining a project's deliverables, goals, tasks, deadlines, and cost and how to develop the software product.

## Slide 3: Project Management
Planning
Estimating
Scheduling
Define activities & deliverables
Time, Cost in terms of resource usage
Define sequence of tasks occurrence

## Slide 4: What is WBS?
a work breakdown structure is:
  “A hierarchical decomposition
  of the total scope of work
  to be carried out by the project team
  to accomplish the project objectives
  and create the required deliverables.”

## Slide 5: WBS
Dividing complex projects to simpler and manageable tasks.
Stops till the tasks no longer remains decomposable.
Work packages: the smallest unit of work that a project can be broken down into.
A WBS element may be a product, data, a service, or any combination.
5

## Slide 6: Why is it needed?
For activities identification
For correct estimation
Identify related activities using PERT
Creating schedules
Project failure risk minimized

## Slide 7: When should we develop WBS?
After finalizing project scope and before project estimation

## Slide 8: How to create WBS?
Done by project managers mostly
describe the project statement
Highlight all necessary phases in the project
Create deliverables
Validate for completeness
8

## Slide 9: WBS

## Slide 10: Reasons to use WBS
correct project organization.
depicts whole project work.
Helpful for describing the project scope to stakeholders.
Helpful in cost estimation, resource allocation, and time management improvements.
Minimize unnecessary work that leads to missed deadlines and out-of-scope work.

## Slide 11: Levels in WBS
Starts with level 0 i.e. project title
Then make level 1, highest level breakdown of about 4-7 nodes depending on your project. Termed as control accounts
Then make level 2, they are work packages.
Level 3 are the tasks/activities to be performed
Follow the standard numbering scheme
11

## Slide 12: WBS Formats
Outline (Indented Format)
Graphical Tree (Organizational Chart)

## Slide 13: Displaying the WBS Example of outlined WBS.
13

## Slide 14: Displaying the WBS Example of Graphical Tree WBS
14

## Slide 15: Challenges
Must have concrete knowledge of project
All tasks/ deliverables properly identified and quoted
Each task should be broken down into legit activities
15

## Slide 16: WBS Guidelines
16
Must be easy to understand
Covers all objectives
Each element corresponds to a deliverable
Breakdown until you get accurate time and cost estimates
Should not be much detailed as project plan
Can evolve over time
Each level have no more than 7 items
Can be drawn using Gantt Pro, Word, Excel, MS Project, Visio etc. May use a template if you have

## Slide 17: Example WBS
Redecorate Room
  Prepare materials
    Buy paint
    Buy a ladder
    Buy brushes/rollers
    Buy wallpaper remover
  Prepare room
    Remove old wallpaper
    Remove detachable decorations
    Cover floor with old newspapers
    Cover electrical outlets/switches with tape
    Cover furniture with sheets
  Paint the room
  Clean up the room
    Dispose or store left over paint
    Clean brushes/rollers
    Dispose of old newspapers
    Remove covers
WBS

## Slide 18: Professional Tools used
https://www.projectmanager.com/
https://www.atlassian.com/software/jira
https://ganttpro.com/